# Smart Prompt Optimization - Project Status Report

Gen AI Micro Project | Status as of 27 October 2026

# 1. Snapshot

All code for the project is written and individually working. The one thing not yet finished is a complete measurement run against the Gemini API, because the API has been unstable and the free-tier quota is very small. The run can be resumed at any time without losing or re-paying for any completed call.

| Component | Status | Evidence |
| --- | --- | --- |
| Code (11 source files) | Complete | - |
| Dataset (13 items) | Complete | - |
| Smoke test (end-to-end) | Passing | 9/9 calls, exit 0 |
| Full sweep (195 calls) | 16% done | 31/195 cached, 164 to go |
| LLM judge pass | Not started | needs sweep results |
| results.csv / summary.json / charts / report.md | Not generated | generated at end of sweep |
| Streamlit dashboard verification | Not run | app.py written, never launched |
| README + requirements.txt | Complete | - |

# 2. What is completed

## 2.1 Planning and specification

Read and understood GenAI_MicroProj.pptx (5 problem-statement objectives).

Project_Implementation_Plan.docx written: tech stack, features F1-F5, dataset design, execution budget, file layout, limitations, out-of-scope list.

## 2.2 Project code (all written and import-clean)

| File | Contents |
| --- | --- |
| src/compressor.py | baseline / lexical / sentence x 7 retention levels (1.0 -> 0.15), TF-IDF sentence ranking, token-level scoring, prompt assembly |
| src/cost.py | pricing table for gemma-4-26b-a4b-it ($0.15/$0.60 per 1M), cost = tokens x price |
| src/llm.py | Gemini client, .env loader, per-call JSON cache, throttle, retries, fail-fast quota detection, cap escalation for runaway generation |
| src/metrics.py | Token-F1 vs reference answer + LLM-as-judge (1-5) |
| src/optimizer.py | run storage, CSV/summary writers, constrained selection (cheapest config with judge >= 4.0 and F1 >= 90% of baseline) |
| src/dataset.py | loader for data/dataset.json |
| main.py | --smoke / --run-all / --report CLI, parallel workers, resume logic, charts, markdown report |
| app.py | Streamlit dashboard: cost/quality charts, Pareto frontier, side-by-side prompt viewer, recommendation card |

## 2.3 Dataset

data/dataset.json: 13 long-prompt QA items (policies, specs, technical docs), roughly 900-1700 tokens each, each with a reference answer for scoring.

## 2.4 Verified working

Compression ratios verified locally: level 0.15 retains ~16% of tokens, level 1.0 is untouched.

Smoke test passes end-to-end against the live API (9/9 calls, no timeouts, exit code 0), including cost, F1 and ratio calculations.

Cache verified: 31 of 195 sweep cells already answered and stored in results/cache.json - these replay instantly and are never re-billed.

requirements.txt and README.md written.

# 3. What is pending, and why

## 3.1 Full measurement sweep (164 of 195 calls remaining)

Why it is pending:

Free-tier quota: the Gemini 3.x models on this key allow only 20 requests per day, which rules them out for a 195-call sweep. The project therefore runs on gemma-4-26b-a4b-it, which has no daily cap but is much less reliable.

Server errors: roughly 1 in 3 calls returns 500 INTERNAL or 504 DEADLINE_EXCEEDED, mostly on lexical-compressed prompts. Each failure is retried 6 times, which stretches the wall-clock time enormously.

Slow calls: gemma runs ~880 hidden thinking tokens per call (~38s each). Observed throughput is about 3.3 calls/minute at 6 workers, so the remaining 164 calls need roughly 50-90 minutes of uninterrupted run time.

The background process died at 14:16 on 26 October (killed along with a timed-out tool session). Completed work was kept in the cache; runs.json is only written when the sweep finishes, so no run records exist yet.

How to finish it:

Run in the background: GENAI_WORKERS=6 GENAI_MIN_INTERVAL=0.2 GENAI_TIMEOUT_MS=240000 python main.py --run-all --resume, and watch results/run.log.

If 500/504 errors persist, drop to 2-3 workers (fewer parallel long requests means fewer server disconnects) - the cache makes restarts free.

## 3.2 LLM judge pass (objective 3, second metric)

Why it is pending:

The judge only scores configurations that exist, so it runs automatically after the sweep inside --run-all (baseline + the top 4 levels per method by token-F1, roughly 40-60 extra calls).

Not started because the sweep itself has not completed.

## 3.3 Generated outputs (objective 5 artifacts)

Why it is pending:

results/results.csv, results/summary.json, results/report.md and the three charts (cost_vs_level.png, quality_vs_level.png, pareto.png) are produced by the final stage of --run-all. They cannot be produced meaningfully from 16% of the data, and the code that writes them only runs at the end of a sweep.

Currently results/ contains only cache.json, run.log and smoke.log.

## 3.4 Streamlit dashboard (objective 4 presentation)

Why it is pending:

app.py is written but has never been launched. It reads results/summary.json and results/runs.json, which do not exist yet, so starting it now would show empty charts.

Verification step after the sweep: streamlit run app.py.

## 3.5 Cleanup

probe_models.py - a temporary diagnostic script used to find a model with usable quota. Should be deleted before submission.

# 4. Known issues and risks

| Issue | Symptom | Cause | Proposed handling |
| --- | --- | --- | --- |
| Lexical compression scores badly | In the smoke test, lexical-compressed prompts produced very low Token-F1 (0.00-0.05) and unusually long answers (2500-4100 output tokens). | Token-level deletion produces fragmentary text; the model then spends its output budget reasoning without finding an answer, which also makes lexical the most expensive and most error-prone cell. | Decision needed: either (a) present it as a genuine negative finding - naive token dropping fails on this model, or (b) soften the compressor to keep grammatical glue. Sentence compression works well (F1 ~0.59 at 45% retention). |
| Cost is simulated | Cost = real token counts x published price, not an actual invoice. | Stated limitation, already in the plan document. | Keep as a stated limitation in the report and the deck. |
| Judge uses the same model family as the generator | Mild self-preference bias in the 1-5 score. | Stated limitation. | Token-F1 is reported alongside the judge score, as planned. |
| Free-tier fragility | 20 requests/day on Gemini 3.x models; 500/504 instability on Gemma. | No paid key available. | Cache + resume make the run interruptible; a run only needs one clean hour. |

# 5. Remaining steps in order

1. Relaunch the sweep in the background with --resume and 6 workers; monitor results/run.log until 195/195.

2. Let the same command run the judge pass automatically (or run 'python main.py --report' later to top it up).

3. Confirm results.csv, summary.json, report.md and the three PNG charts exist; read report.md for the selected configuration.

4. Launch 'streamlit run app.py' and verify the dashboard renders the charts, the prompt viewer and the recommendation card.

5. Decide how to present the lexical-compression result (negative finding vs. compressor tweak).

6. Delete probe_models.py and make sure API_KEY.env is not committed.

# 6. Estimated effort left

Sweep: 50-90 minutes of wall-clock (background, no supervision needed).

Judging: ~10-15 minutes, automatic.

Outputs + charts: automatic, seconds.

Dashboard check: ~5 minutes.

Total hands-on time: about 10 minutes; the rest is waiting on the API.